## WHMcNumber (hidden)
DO NOT ALTER OR DELETE THIS SHEET. | Chart Names | Excel Version | 12

## A3 Thinking
A3 PROJECT MANAGEMENT AND PROBLEM SOLVING THINKING
1. | WHAT IS AN A3 PROJECT?
An activity that
(a) supports achievement of the continuous improvement objectives
(b) requires > 20 hours dedicated man-hours
(c) has an A3 worksheet
2. | WHERE DO A3 PROJECTS COME FROM?
All functions & all personnel entitled to propose projects
Derived from e.g. continuous improvement objectives or VSM or other business critical source e.g. compliance requirement or safety requirement
All projects pre-screened by snr managers prior to proposal for the master list
The master project list is maintained by the continuous improvement facilitator
3. | A3 OBJECTIVE
To provide a one page (A3, 420mm x 297mm) summary of a programme, project or problem, for the project team & relevant personnel within the organisation
4. | WHY?
Encourages brevity & sharpness of thinking
Tells a logical story on one sheet for all viewers
Provides a common organisation-wide format for all programme, management, project managment & problem solving activities
5. | WHO?
Team leader of the programme or project, or process owner of the area under review
6. | HOW?
Completion of the standard A3 Template. The template usually consistes of 7 to 9 boxes with standard input requirements, that follow the 8 stpe path. The template is modified to suit individual projects.
Use photographs, drawings & graphs to tell the story
7. | UPDATE FREQUENCY
The A3 is a living document and is updated as the team moves through the stages of the project
8. | REVIEW FREQUENCY
The A3 document is reviewed by the team and programme or project champion on an as-required basis during the project lifespan. Review frequencies are determined at the start of the project.

## A3 Steps
TOYOTA 8 STEP PROBLEM SOLVING PROCESS
Step and objective | Tools used
Step 1: Clarify the Problem
Why am I looking at this problem? What is the problem? Who is interested in the problem? What benefit does solving this problem have for me? How does it help to address the goals of the business? | Voice of the customer
Stakeholder analysis
Is/is not analysis
Step 2: Breakdown the Problem
What is the size of the problem? What data do I have? What are the component parts of this problem? How much will I address at this point? | SIPOC, process mapping, spaghetti mapping, data collection, run chart, bar chart, histogram, box plot
Step 3: Set the Target.
What outcome do I want? Visualise the desired results. Using the data, set a measurable and realistic goal. | Goal setting. Agreement with stakeholders on outcome
Step 4: Analyse the Root Cause
Clarify the root cause. Consider as many potential cause factors as possible. | Interviews, 5 whys, cause and effects analysis, regression & correlation, process capability analysis
Step 5: Develop Countermeasures
List as many potential countermeasures as possible. Identify an effective countermeasure that directly addresses the root cause. | Brainstorming
Team discussion
Step 6: Pick a Countermeasure and implement
Select the most practical and effective countermeasure. Create a clear and detailed action plan. Implement quickly. | Action plan
Gantt chart
Step 7: Monitor Results & Process
Monitor progress and report findings to stakeholders. It may require more than one attempt to get the desired result. Mistakes are an important part of the learning process. | Run chart, control chart
Step 8: Standardise & Share Success
Document the new process and set as new standard. Share the new standard through Horizontal deployment. Reflect and celebrate success. Start the next Improvement! | Standard work

## A3 Template
A3 No. and Name | Team members (name & role) | Stakeholders (name & role) |  | Department | Organisation objective
| 1. | 1.
| 2. | 2.
Team Leader (name & 'phone ext) | 3. | 3. |  |  | Start date & planned duration
| 4. | 4.
1. Clarify the problem |  | 4. Analyse the Root Cause |  |  | 7. Monitor Results & Process
Is:
Is not:
Problem statement:
2. Breakdown the problem
8. Standardise & Share Success
5. Develop Countermeasures
|  |  | Countermeasure | Impact on target
1
2
3
6. Implement Countermeasure
3. Set the Target
1
2
3
4
Note on B2: use standard project numbering system (e.g. 2011-XX) and simple short name
Note on B8: 1. Clarify the problem Why am I looking at this problem? What is the problem? Who is interested in the problem? What benefit does solving this problem have for me? How does it help to address the goals of the business? Select the area/process & open A3 in Excel Elect a leader Form the team (stakeholders) Train the team in the 8 step approach Identify all stakeholders Define the problem in terms of impact on the customer & stakeholders. Conduct is/is not analysis Conduct a gemba walk and take photographs
Note on H8: 4. Analyse the Root cause Clarify the root cause. Consider as many potential cause factors as possible. - Interviews - praetor charts - Data stratification - 5 whys - Cause and effects analysis - Process Capability Analysis - Scatter diagrams - Box plots - Regression & Correlation - FMEA Identify areas for improvement
Note on N8: 6. Monitor Results & Process Monitor progress and report findings to stakeholders. It may require more than one attempt to get the desired result. Mistakes are an important part of the learning process. - Run chart - Control chart - Process capability analysis Conduct post implementation review - snag list & action items
Note on B22: 2. Breakdown the problem What is the size of the problem? What data do I have? What are the component parts of this problem? How much will I address at this point? Draft a summary map of process, or machine schematic e.g. - SIPOC - Spaghetti map - process map - blueprint Measure key features of the process problem e.g. - Bar chart - line graph - Run chart
Note on N27: 8. Standardise & Share Success Document the new process and set as new standard. Share the new standard through Horizontal deployment. Reflect and celebrate success. - Train personnel in new way of doing things - Standardise new processes, update procedures, implement visual management - Use control charting to prove results and maintain discipline in th area - Confirm the financial gains (if required) - Present to senior management - Recognise and reward the team - Reflect on lesson learned Start the next Improvement!
Note on H33: 5. Develop Countermeasures List as many potential countermeasures as possible. Identify an effective countermeasure that directly addresses the root cause. Prioritise issues Identify and make ready all tools an equipment for change in advance of the of the event - Brainstorming - Priority list - Gantt chart - Pilot timetable
Note on H42: 5. Pick a Countermeasure & implement Select the most practical and effective countermeasure(s). Create a clear and detailed action plan. Implement quickly. - Gantt chart - tasks and timelines - Detailed timetable of events - layout changes - SMED - visual workplace - error proofing - FMEA
Note on B44: 3. Set the target What outcome do I want? Visualise the desired results. Using the data, set a measurable and realistic goal. Goal format: Action verb + object of the action + from "current state" + to "future state" by "date" e.g. Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 January 2014" Draft the outline project plan by when the project will be finished Allocate time lines & responsibilities (e.g. summary Gantt chart) Develop draft financial gains and get finance approval (if appropriate)

## A3 Toast Example
A3 No. and Name |  | Stakeholders (name & role) | Team members (name & role) |  | Department |  | Company objective
A3-12345 B |  | 1. | 1. |  |  | The Kitchen | Domestic harmony
|  | 2. | 2.
Team Leader (name & 'phone ext) |  | 3. | 3. |  |  |  | Start date & planned duration
|  | 4. | 4.
1. Clarify the problem |  |  | 4. Analyse the Root Cause |  |  |  | 7. Monitor Results & Process
Is: | The Kitchen, toast making process for wife
Is not: any other part of the house, any other cooking process, the washing up
Problem statement:
Bruce's time and resources (bread, butter & energy) are being wasted in the process of making toast that fails to meet his wife's requirements. As a result the process needs to be repeated.
2. Breakdown the problem
[6 empty] | Cause & effects conclusions: | 8. Standardise & Share Success
Customer not asked
Distance between toaster, bread, plates & knife is too long
Butter too hard
Bruce also managed to get the dishwasher filled and running in the 2mins and 17secs it now takes him to make the toast.
5. Develop Countermeasures
|  |  |  | Countermeasure | Impact on target
|  |  | 1 | Ask the customer what she wants | Correct inventory, no dumping, RFT 100% |  | Domestic harmony is increased :)
|  |  | 2 | Move toaster near plates & bread | Distance: minus 12 metres |  | 1. | Lean is a different way of looking at things. Focus on the process, and WASTE in the process, not the individual carrying out the process
Time: minus 1 min
|  |  | 3 | Have spreadable butter ready | Distance: minus 6 metres
[5 empty] | Time: minus 20 seconds |  | 2. | We need to immediately address the position of the toaster under the paper towel - safety hazard!!!
Washing up is outside the scope as we reckon Bruce won't have time.
6. Implement Countermeasure
[7 empty] | 3. | The fridge position needs to be raised to better ergonomic height and contents de cluttered
3. Set the Target
1 | Improve customer RFT from 0% to 100%
2 | Reduce the toast making process time from 4mins 12 secs to 3 mins
3 | Reduce the distance travelled during toast making from 21.5 metres to 10 metres
4
Note on B2: use standard project numbering system (e.g. 2011-XX) and simple short name
Note on B8: 1. Clarify the problem Why am I looking at this problem? What is the problem? Who is interested in the problem? What benefit does solving this problem have for me? How does it help to address the goals of the business? Select the area/process & open A3 in Excel Elect a leader Form the team (stakeholders) Train the team in the 8 step approach Identify all stakeholders Define the problem in terms of impact on the customer & stakeholders. Conduct is/is not analysis Conduct a gemba walk and take photographs
Note on H8: 4. Analyse the Root cause Clarify the root cause. Consider as many potential cause factors as possible. - Interviews - praetor charts - Data stratification - 5 whys - Cause and effects analysis - Process Capability Analysis - Scatter diagrams - Box plots - Regression & Correlation - FMEA Identify areas for improvement
Note on N8: 6. Monitor Results & Process Monitor progress and report findings to stakeholders. It may require more than one attempt to get the desired result. Mistakes are an important part of the learning process. - Run chart - Control chart - Process capability analysis Conduct post implementation review - snag list & action items
Note on B20: 2. Breakdown the problem What is the size of the problem? What data do I have? What are the component parts of this problem? How much will I address at this point? Draft a summary map of process, or machine schematic e.g. - SIPOC - Spaghetti map - process map - blueprint Measure key features of the process problem e.g. - Bar chart - line graph - Run chart
Note on N24: 8. Standardise & Share Success Document the new process and set as new standard. Share the new standard through Horizontal deployment. Reflect and celebrate success. - Train personnel in new way of doing things - Standardise new processes, update procedures, implement visual management - Use control charting to prove results and maintain discipline in th area - Confirm the financial gains (if required) - Present to senior management - Recognise and reward the team - Reflect on lesson learned Start the next Improvement!
Note on H30: 5. Develop Countermeasures List as many potential countermeasures as possible. Identify an effective countermeasure that directly addresses the root cause. Prioritise issues Identify and make ready all tools an equipment for change in advance of the of the event - Brainstorming - Priority list - Gantt chart - Pilot timetable
Note on H38: 5. Pick a Countermeasure & implement Select the most practical and effective countermeasure(s). Create a clear and detailed action plan. Implement quickly. - Gantt chart - tasks and timelines - Detailed timetable of events - layout changes - SMED - visual workplace - error proofing - FMEA
Note on B40: 3. Set the target What outcome do I want? Visualise the desired results. Using the data, set a measurable and realistic goal. Goal format: Action verb + object of the action + from "current state" + to "future state" by "date" e.g. Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 January 2014" Draft the outline project plan by when the project will be finished Allocate time lines & responsibilities (e.g. summary Gantt chart) Develop draft financial gains and get finance approval (if appropriate)

## Is-Is Not
IS /IS NOT ANALYSIS
Used to develop a problem statement and define the scope of a project.
Description | IS (Observation): | IS NOT (Observation): | NOTES
What is the defect?
What processes?
Where in the process ?
Who is affected?
When did it happen?
How frequently did it happen?
Is there a pattern?
How much is it costing?
Problem Statement: (from the IS column):

## Goal setting
GUIDELINES FOR WRITING A CLEAR, RESULTS FOCUSED GOAL
Sequence | Activity | Example
Start with | Action verb | Increase
add | object of the action | The right first time on application forms
add | from current state | from 50%
add | to future state | to 75%
finish with completion date | by mm/dd/yyyy | by 31 March 2013
e.g. "Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 Jaunary 2014"

## Fishbone template
Cause and Effect Diagram
|  |  |  | Prepared by: |  | _________________________
| manpower |  | customer |  | machine
Bruce |  | Sophia, the customer |  | Utensils
Inefficient toast making process giving zero customer satisfaction
Toaster |  | The process |  | Bread & butter
| machine |  | method |  | materials
Add Item
Add Sub Item